## Project Launch Plan
Task Name | Status | Health | Start Date | End Date | Assigned To | Description | Duration | Predecessors | % Complete | % Allocation | Images
HR System Timeline |  |  | 2020-02-09 | 2020-05-13 |  |  | 69d |  | 8%
Planning Phase |  |  | 2020-02-09 | 2020-03-24 |  |  | 33d |  | 6%
Scope | Complete | Green | 2020-02-09 | 2020-02-13 | TeamGrammers |  | 5d |  | 10% | 100%
Analysis/Software Requirements | Complete | Green | 2020-02-13 | 2020-03-04 | TeamGrammers |  | 15d | 3FS -1d | 10% | 100%
Design | Complete | Green | 2020-03-04 | 2020-03-24 | TeamGrammers |  | 15d
Implement Phase |  |  | 2020-03-25 | 2020-05-05 |  |  | 30d |  | 24%
Development | Complete | Green | 2020-03-25 | 2020-04-28 | TeamGrammers |  | 25d |  | 50% | 100%
Testing | Complete | Green | 2020-03-25 | 2020-05-05 | TeamGrammers |  | 30d |  | 25% | 100%
Documentation | Complete | Green | 2020-03-25 | 2020-05-05 | TeamGrammers |  | 30d
Pre-Release Phase |  |  | 2020-03-04 | 2020-05-05 | TeamGrammers |  | 45d
Training | Complete | Green | 2020-03-25 | 2020-05-05 | TeamGrammers |  | 30d
Pilot | Complete | Green | 2020-03-04 | 2020-05-05 | TeamGrammers |  | 45d
Release Phase |  |  | 2020-05-02 | 2020-05-13 | TeamGrammers |  | 9d
Deployment | Complete | Green | 2020-05-02 | 2020-05-05 | TeamGrammers |  | 3d
Post Implementation Phase | Complete | Green | 2020-05-11 | 2020-05-13 | TeamGrammers |  | 3d